## Switch
Table description | 单元格中黑色字体FW/HW版本为PP要求DV7支持的设备版本；红色字体表示DV7已支援的设备FW/HW版本
Model | PP | FW | HW | Schedule | Status | Fail Note | D-View 7 Beta Ver. | PIC | Note
DGS-1210-10/ME | Abbie | v7.01.045 | B1 | 2016-11-21 | Pass |  | 1.2.2.3
DGS-1210-10/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016-12-27 | Pass |  | 1.2.2.3 |  | log: 2016/8/5; 6.12.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-10P/ME | Abbie | v7.01.045 | B1 | 2016-11-16 | Pass |  | 1.2.2.3
DGS-1210-10P/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016-12-20 | Pass |  | 1.2.2.3 |  | log: 2016/7/22; 6.12.B031; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-12TS/ME | Abbie | v7.01.045 | B1 | 2016-11-15 | Pass |  | 1.2.2.3 |  | log: 2016/8/12; 7.01.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-20/ME | Abbie | v7.01.045 | B1 | 2016-12-05 | Pass |  | 1.2.2.3
DGS-1210-20/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016-12-16 | Pass |  | 1.2.2.3 |  | log: 2016/7/22; 6.12.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-28/ME | Abbie | v7.01.045 | B1 | 2016-10-20 | Pass |  | 1.2.2.3 |  | 彰化教網
DGS-1210-28/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016-11-11 | Pass |  | 1.2.2.3
DGS-1210-28P | Abbie | 4.10.004 | C1 | 2016-12-19 | Pass |  | 1.2.2.4 |  | log: 4.00.016; Test Restore only; DV7: 1.0.3.9
DGS-1210-28P/ME | Abbie | v7.01.045 | B1 | 2016-11-24 | Pass |  | 1.2.2.3
DGS-1210-28P/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016-12-26 | Pass |  | 1.2.2.3 |  | log: 2016/7/29; 6.12.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-28X/ME | Abbie | v7.01.045 | B1 | 2016-11-15 | Pass |  | 1.2.2.3 |  | log: 2016/8/17; 7.01.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-52/ME | Abbie | v7.01.045 | B1 | 2016-11-29 | Pass |  | 1.2.2.3
DGS-1210-52/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016-12-22 | Pass |  | 1.2.2.3 |  | log: 2016/7/29; 6.12.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-52MP/ME | Abbie | v7.01.045 | B1 | 2016-12-02 | Pass |  | 1.2.2.3
DGS-1210-52MP/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016-12-29 | Pass |  | 1.2.2.3 |  | log: 2016/8/12; 6.12.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-52MPP/ME | Abbie | v7.01.045 | B1 | 2016-12-13 | Pass |  | 1.2.2.3
DGS-1210-52P/ME | Abbie | v7.01.045 | B1 | 2016-12-08 | Pass |  | 1.2.2.3
DGS-1210-52P/ME | Abbie | v6.12.B044/v6.12.B045 | A1 | 2016/12/28 | Pass |  | 1.2.2.3 |  | log: 2016/8/5; 6.12.B022; Restore, FW upgrade Failed, DV7:1.2.2.1
DGS-1210-10 | Abbie | 4.10.004/4.00.055 | C1 |  | Pass |  | 1.0.3.9
DES-1210-10/ME | Abbie | v6.09.B046 | B1 | 2017-02-27 | pass |  | 1.3.0.0
DES-1210-10/ME | Abbie | v10.04.B017 | B2 | 2017-02-27 | pass | fw upgrade not support | 1.3.0.0
DGS-1210-10P | Abbie | 4.10.004 | C1 |  | Pass |  | 1.2.0.0
DES-1210-28/ME | Abbie | v10.04.B017 | B3 | 2017-02-27 | pass | fw upgrade not support | 1.3.0.0
DGS-1210-20 | Abbie | 4.10.004 | C1 |  | Pass |  | 1.2.0.0
DES-1210-52/ME | Abbie | v20.03.B017 | C1 | 2017-02-27 | pass | fw upgrade not support | 1.3.0.0
DGS-1210-28 | Abbie | 4.10.004 | C1 |  | Pass |  | 1.2.0.0
DGS-1210-28MP | Abbie | v5.00.017 | E1 |  | Pass |  | 1.2.2.1
DGS-1210-28MP/ME | Abbie | v7.01.045 | B1 |  | Pass |  | 1.2.2.0
DGS-1210-28XS/ME | Abbie | v7.01.045/7.01.B031 | B1 |  | Pass |  | 1.2.2.1
DGS-1210-52 | Abbie | 4.10.004/4.00.025 | C1 |  | Pass |  | 1.0.3.9
DGS-1210-52MP | Abbie | v5.00/4.00.057 | E1/C1 |  | Pass |  | 1.0.3.9
DGS-1210-52MPP | Abbie | v5.00.017 | E1 |  | Pass |  | 1.2.2.1
DGS-1210-52P | Abbie | 4.10.004/4.00.055 | C1 |  | Pass |  | 1.0.3.9
DXS-1100-16SC | Fucherng | 1.00.005 | A1 | 2017-01-16 | Fail | Device will reboot when DV7 set SNMP request to it.(Device Issue) | 1.3.0.1
DGS-1510-28LP/ME | Fucherng | 1.10.010 | A1 | 2017-02-06 | pass |  | 1.3.0.0
DGS-1510-28L/ME | Fucherng | 1.10.010 | A1 | 2017-01-23 | pass |  | 1.3.0.0
DGS-1510-28X/ME | Fucherng | 1.10.010 | A1 | 2017-02-14 | pass |  | 1.3.0.0
DGS-1510-28XMP/ME | Fucherng | 1.10.010 | A1 | 2017-02-17 | pass |  | 1.3.0.0
DXS-1100-10TS | Fucherng | 1.10.006 | A1 | 2017-01-16 | pass |  | 1.3.0.0
DXS-1100-16TC | Fucherng | 1.10.006 | A1 | 2017-01-16 | pass |  | 1.3.0.0
DGS-1510-52X/ME | Fucherng | 1.10.010 | A1 | 2017-02-22 | pass |  | 1.3.0.0
DGS-1510-10L/ME | Fucherng | 1.00.018 | A1 |  | Pass |  | 1.0.3.4
DGS-1510-20 | Fucherng | 1.10.005/1.30.007 | A1 |  | Pass |  | 1.0.2.1
DGS-1510-20L/ME | Fucherng | 1.00.018 | A1 |  | Pass |  | 1.0.3.4
DGS-1510-28 | Fucherng | 1.10.005 | A1 |  | Pass |  | 1.0.2.1
DGS-1510-28P | Fucherng | 1.10.005 | A1 |  | Pass |  | 1.0.2.1
DGS-1510-28X | Fucherng | 1.10.005 | A1 |  | Pass |  | 1.0.2.1
DGS-1510-28XMP | Fucherng | 1.10.005/1.20.011 | A1 |  | Pass |  | 1.0.2.4
DGS-1510-28XS/ME | Fucherng | 1.00.018 | A1 |  | Pass |  | 1.0.3.4
DGS-1510-52 | Fucherng | 1.10.005 | A1 |  | Pass |  | 1.0.2.1
DGS-1510-52L/ME | Fucherng | 1.00.018 | A1 |  | Pass |  | 1.0.3.4
DGS-1510-52X | Fucherng | 1.10.005/1.00.004 | A1 |  | Pass |  | 1.0.2.1
DWC-2000 | Howard Kao | 4.4.0.3_B920/4.4.0.2_B501_WW | A1 |  | Pass |  | 1.0.2.1
DSR-1000AC | Jeff | 3.08B011E/3.08B009E | A1 |  | Pass |  | 1.1.0.1
DWR-925 | Jerry | V1.06b13 | B1 |  | Pass |  | 1.2.0.0
DGS-1100-06/ME | Shuochun | 1.04.B014/1.00.010 | A1 | 2017-04-10 | pass |  | 1.3.0.1 |  | log: Dev FW:1.00.010; Status:Failed 1Restore config Fail: Device needs to reboot; DV7:1.0.2.1 -------------------------- delay due to RD prepare 1.3.0.0 release, adjust the schedule again and start from 2017/4/10 DV7:1.3.0.0
DGS-1100-10/ME | Shuochun | 1.01.B049/1.01.B015 | A1 | 2017-04-10 | failed | restore need to manually reboot(Device problem) | 1.3.0.1 |  | log: Dev FW:1.01.B015; Status:Failed 1Restore config Fail: Device needs to reboot; DV7:1.0.2.1 -------------------------- delay due to RD prepare 1.3.0.0 release, adjust the schedule again and start from 2017/4/10 DV7:1.3.0.0
DGS-1100-18/ME | Shuochun | 1.00.B026 | B1 | 2017-04-10 | failed | restore failed(Device problem) | 1.3.0.1 |  | log: delay due to RD prepare 1.3.0.0 release, adjust the schedule again and start from 2017/4/10 DV7:1.3.0.0
DGS-1100-24/ME | Shuochun | 1.00.B026 | B1 | 2017-04-10 | failed | restore failed(Device problem) | 1.3.0.1 |  | log: delay due to RD prepare 1.3.0.0 release, adjust the schedule again and start from 2017/4/10 DV7:1.3.0.0
DGS-1100-24P/ME | Shuochun | 1.00.B027 | B1 | 2017-07-27 | pass |  | 1.3.0.1
DGS-1100-26/ME | Shuochun | 1.00.B026 | B1 | 2017-04-10 | failed | restore failed(Device problem) | 1.3.0.1 |  | log: delay due to RD prepare 1.3.0.0 release, adjust the schedule again and start from 2017/4/10 DV7:1.3.0.0
DES-1210-08P | Jessica | v4.11.B029 | C2 | 2017-02-20 | pass |  | 1.3.0.0
DGS-1100-16/ME | Shuochun | 1.00.B026 | B1 | 2017-04-10 | NT | no device | 1.3.0.1 |  | log: delay due to RD prepare 1.3.0.0 release, adjust the schedule again and start from 2017/4/10 DV7:1.3.0.0
DGS-3120-24TC | Joshua | 3.10.B028 | A2 | 2017-04-17 | NT | No device can be used to test, PP confirmed all this series devices use the same FW code | 1.3.0.1
DGS-3120-48TC | Joshua | 3.10.B028 | A2 | 2017-04-17 | NT | No device can be used to test, PP confirmed all this series devices use the same FW code | 1.3.0.1
DGS-3120-24PC | Joshua | 3.10.B028 | A2 | 2017-04-17 | NT | No device can be used to test, PP confirmed all this series devices use the same FW code | 1.3.0.1
DES-1210-28 | Jessica | v4.10.B025 | C1 | 2017-02-20 | pass |  | 1.3.0.0
DES-1210-28P | Jessica | v4.12.B029 | C2 | 2017-02-20 | pass |  | 1.3.0.0
DGS-3120-24SC-DC | Joshua | 3.10.B028 | A2 | 2017-04-17 | NT | No device can be used to test, PP confirmed all this series devices use the same FW code | 1.3.0.1
DES-1210-52 | Jessica | v4.10.B025 | C1 | 2017-02-20 | pass |  | 1.3.0.0
DES-3200-10-DC | Jessica | v4.46.B003 | C1 | 2017-03-06 | pass |  | 1.3.0.0
DES-3200-18-DC | Jessica | v4.46.B003 | C1 | 2017-03-06 | pass |  | 1.3.0.0
DES-3200-26-DC | Jessica | v4.46.B003 | C1 | 2017-03-06 | pass |  | 1.3.0.0
DES-3200-28-DC | Jessica | v4.05.004 | C1 | 2017-03-06 | NT | No Sample can be used to test | -
DES-3200-28F | Jessica | v4.46.B003 | C1 | 2017-03-06 | pass |  | 1.3.0.0
DES-3200-52-DC | Jessica | v4.05.004 | C1 | 2017-03-06 | NT | No Sample can be used to test | -
DES-3200-10 | Jessica | v4.05.004/4.02.004 | C1 |  | Pass |  | 1.0.1.9
DES-3200-18 | Jessica | v4.05.004/4.04.004 | C1 |  | Pass |  | 1.0.2.1
DES-3200-26 | Jessica | v4.05.004/4.04.004 | C1 |  | Pass |  | 1.0.2.1
DES-3200-28 | Jessica | v4.05.004/4.04.004 | C1 |  | Pass |  | 1.0.1.9
DES-3200-28/ME | Jessica | v4.05.004/4.04.004 | C1 |  | Pass |  | 1.0.2.1
DES-3200-28P | Jessica | v4.05.004/4.04.004 | C1 |  | Pass |  | 1.0.1.9
DES-3200-52 | Jessica | v4.05.004/4.00.020 | C1 |  | Pass |  | 1.0.2.0
DES-3200-52P | Jessica | v4.05.004/4.04.004 | C1 |  | Pass |  | 1.0.1.9
DES-3528 | Jessica | v3.00.012 | A5/A2 |  | Pass |  | 1.0.1.9
DGS-1100-10MP | Jimmy | 1.00.B013 | B1 | 2016-06-24 | Pass |  | 1.2.0.0
DGS-1100-10MPP | Jimmy | 1.00.B013/1.00.B005 | B1 | 2016-07-01 | Pass |  | 1.2.0.0
DGS-1100-26MP | Jimmy | 1.00.B013 | B1 | 2016-07-01 | Pass |  | 1.2.0.0
DGS-1100-26MPP | Jimmy | 1.00.B013 | B1 | 2016-07-01 | Pass |  | 1.2.0.0
DGS-1210-08P | Jimmy | V4.22.B001 | D2 | 2016-10-31 | Pass |  | 1.2.2.3
DGS-1210-16 | Jimmy | V4.22.B001 | D1 | 2016-11-03 | Pass |  | 1.2.2.3
DGS-1210-24 | Jimmy | V4.22.B001 | D1 | 2016-10-12 | Pass |  | 1.2.2.3 |  | Change priority for DEU customer
DGS-1210-24P | Jimmy | V4.22.B001 | D1/D2 | 2016-10-17 | Pass |  | 1.2.2.3 |  | Change priority for DEU customer
DGS-1210-48 | Jimmy | V4.22.B001 | D1 | 2016-11-08 | Pass |  | 1.2.2.3
DGS-3000-10TC | Joshua | 2.00.006 | A2 | 2017-02-06 | pass |  | 1.3.0.0
DGS-3000-24TC | Joshua | 2.00.006 | A2 | 2017-02-06 | pass |  | 1.3.0.0
DGS-3000-26TC | Joshua | 2.00.006 | A2 | 2017-02-06 | pass |  | 1.3.0.0
DGS-3120-48PC | Joshua | 3.10.B028 | A2 | 2017-04-17 | pass |  | 1.3.0.1
DGS-3120-24SC | Joshua | 3.10.B028 | A2 | 2017-04-17 | pass |  | 1.3.0.1
DGS-1210-10 | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.2
DGS-1210-10MP | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.2
DGS-1210-10P | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.2
DGS-1210-20 | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.2
DGS-3000-10TC | Joshua | 1.10.013 | A1 |  | Pass |  | 1.1.0.5
DGS-3000-24TC | Joshua | 1.10.013 | A1 |  | Pass |  | 1.1.0.5
DGS-3000-26TC | Joshua | 1.10.013 | A1 |  | Pass |  | 1.1.0.5
DGS-3000-28SC | Joshua | 5.00.020/5.00.B029 | A1 |  | Pass |  | 1.0.3.9
DGS-3120-24PC | Joshua | 4.00.015/3.00.522 | B1 |  | Pass |  | 1.0.2.4
DGS-3120-24SC | Joshua | 4.00.015/3.10.512 | B1 |  | Pass |  | 1.0.2.4
DGS-3120-24SC-DC | Joshua | 4.00.015/3.10.512 | B1 |  | Pass |  | 1.0.2.4
DGS-3120-24TC | Joshua | 4.00.015 | B1 |  | Pass |  | 1.0.2.4
DGS-3120-48PC | Joshua | 4.00.015/3.00.522 | B1 |  | Pass |  | 1.0.2.4
DGS-3120-48TC | Joshua | 4.00.015/3.00.522 | B1 |  | Pass |  | 1.0.2.4
DXS-1210-16TC | Kevin | 1.10.007 | A1 | 2017-02-06 | pass |  | 1.3.0.0 |  | log: Dev FW:1.10.007; Status:Fail 1.Firmware file transfer failed, device return 'unknown' 2. Restore config Fail: Device needs to reboot; DV7:1.2.2.1
DXS-1210-10TS | Kevin | 1.10.013/V1.30.B08 | A1 |  | Pass |  | 1.2.2.1
DXS-1210-12SC | Kevin | 1.10.013/V1.30.B08 | A1 |  | Pass |  | 1.2.2.1
DXS-1210-12TC | Kevin | 1.10.013/V1.30.B08 | A1 |  | Pass |  | 1.2.2.1
DXS-3400-24SC | Peter | 2.00.009 | A1 | 2016-12-26 | Pass |  | 1.2.2.4 |  | log: 1.00.037,Pass;DV7: 1.2.0.0
DXS-3400-24TC | Peter | 2.00.009 | A1 | 2016-12-21 | Pass |  | 1.2.2.4 |  | log: 1.00.037,Pass;DV7: 1.2.0.0
DXS-3600-16S | Peter | 2.40.046 | B1 |  | Pass |  | 1.2.0.0
DXS-3600-32S | Peter | 2.40.046 | B1 |  | Pass |  | 1.2.0.0
DGS-3620-28PC | Shuochun | 2.70.B002 | A1/B1 | 2017-01-03 | Fail | In 2.70.B002 Backup Failed: The file size can be devided exactly by 512KB; 2.70.B004 OK | 1.2.2.4 |  | 2014/10/29; 2.50.017; Pass; DV7:1.0.2.0
DGS-3620-28SC | Shuochun | 2.70.B002 | A1/B1 | 2017-01-05 | Fail | In 2.70.B002 Backup Failed: The file size can be devided exactly by 512KB; 2.70.B004 OK | 1.2.2.4 |  | 2014/10/29; 2.50.017; Pass; DV7:1.0.2.0
DGS-3620-28TC | Shuochun | 2.70.B002 | B1/A1 | 2017-01-09 | Fail | In 2.70.B002 Backup Failed: The file size can be devided exactly by 512KB; 2.70.B004 OK | 1.2.2.4 |  | 2014/10/29; 2.50.017; Pass; DV7:1.0.1.9
DGS-3620-52T | Shuochun | 2.70.B002 | A1/B1(B1) | 2017-01-11 | Fail | In 2.70.B002 Backup Failed: The file size can be devided exactly by 512KB; 2.70.B004 OK | 1.2.2.4 |  | 2014/10/29; 2.50.017; Pass; DV7:1.0.1.9
DGS-3620-52P | Shuochun | 2.70.B002 | A1/B1(B1) | 2017-01-13 | Fail | In 2.70.B002 Backup Failed: The file size can be devided exactly by 512KB; 2.70.B004 OK | 1.2.2.4 |  | 2014/10/29; 2.50.017; Pass; DV7:1.0.2.0
DGS-1210-26 | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.3
DGS-1210-28 | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.3
DGS-1210-28MP | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.3
DGS-1210-28P | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.3
DGS-1210-52 | Jessica | 6.00.011 | F1 | 2017-04-27 | pass |  | 1.3.0.3
DGS-1210-52MP | Jessica | 6.00.B017 | F1 | 2017-04-27 | pass |  | 1.3.0.3
DGS-3630-28SC | Shuochun | 1.00.032 | A1 | 2017-02-06 | pass |  | 1.2.2.5 |  | log: Dev FW:1.00.032; Status:Fail 1.Failed to select the next boot image when firmware upgrade, DV7 need to modified the upgrade mechansim 2.trap host created failed DV7 cannot support G2 devices host create DV7:1.2.2.1
DMC-1002 | Jessica | v2.03 | B1 | 2017-04-27 | NT | no device | 1.3.0.3
DGS-3630-28TC | Shuochun | 1.00.032 | A1 | 2017-02-06 | pass |  | 1.2.2.5 |  | log: Dev FW:1.00.032; Status:Fail 1.Failed to select the next boot image when firmware upgrade, DV7 need to modified the upgrade mechansim 2.trap host created failed DV7 cannot support G2 devices host create DV7:1.2.2.1
DGS-3630-52TC | Shuochun | 1.00.032 | A1 | 2017-02-06 | pass |  | 1.2.2.5 |  | log: Dev FW:1.00.032; Status:Fail 1.Failed to select the next boot image when firmware upgrade, DV7 need to modified the upgrade mechansim 2.trap host created failed DV7 cannot support G2 devices host create DV7:1.2.2.1
DGS-1100-16 | Shuochun | 1.00.B032/1.01.B032 | B1 | 2016-06-24 | Pass |  | 1.2.0.0
DGS-1100-18 | Shuochun | 1.00.B032/1.01.B032 | B1 | 2016-06-24 | Pass |  | 1.2.0.0
DGS-1100-24 | Shuochun | 1.00.B032/1.01.B032 | B1 | 2016-06-24 | Pass |  | 1.2.0.0
DGS-1100-24P | Shuochun | 1.00.B032/1.01.B032 | B1 | 2016-06-24 | Pass |  | 1.2.0.0
DGS-1100-26 | Shuochun | 1.00.B032/1.01.B032 | B1 | 2016-06-24 | Pass |  | 1.2.0.0
DGS-3420-26SC | Shuochun | 1.50.018/1.00.023 | B1/A1 |  | Pass |  | 1.0.2.0
DGS-3420-28PC | Shuochun | 1.50.018/1.00.024 | B1/A1 |  | Pass |  | 1.0.2.0
DGS-3420-28SC | Shuochun | 1.50.018/1.00.023 | B1/A1 |  | Pass |  | 1.0.2.0
DGS-3420-52P | Shuochun | 1.50.018 | B1/A1 |  | Pass |  | 1.0.1.9
DGS-3420-52T | Shuochun | 1.50.018 | B1/A1 |  | Pass |  | 1.0.1.9
DGS-1100-05 | Shuochun | v1.00.016 | B1 | 2017-05-11 | pass |  | 1.3.0.3
DGS-1100-05PD | Shuochun | v1.00.016 | B1 | 2017-05-11 | pass |  | 1.3.0.3
DGS-1100-08 | Shuochun | v1.00.016 | B1 | 2017-05-11 | pass |  | 1.3.0.3
DGS-1100-08P | Shuochun | v1.00.016 | B1 | 2017-05-11 | pass |  | 1.3.0.3
DGS-1100-08PD | Shuochun | 1.00.006 | B1 | 2017-05-16 | pass |  | 1.3.0.3
DXS-1210-10TS | Kevin | v.1.15.005 | A2 | 2017-09-18 | failed | 设备Upgrade时需要自动选择适当的Next Boot Image | 1.3.2.0
DXS-1210-12TC | Kevin | v.1.15.005 | A2 | 2017-09-18 | failed | 设备Upgrade时需要自动选择适当的Next Boot Image | 1.3.2.0
DXS-1210-12SC | Kevin | v.1.15.005 | A2 | 2017-09-18 | failed | 设备Upgrade时需要自动选择适当的Next Boot Image | 1.3.2.0
DXS-1210-16TC | Kevin | v.1.15.009 | A2 | 2017-09-18 | failed | 设备Upgrade时需要自动选择适当的Next Boot Image和devFwOperationImageId | 1.3.2.0
DGS-3630-28PC | Shuochun | 2.00.B021 | A1 | 2017-09-25 | pass |  | 1.3.4.0
DGS-3630-52PC | Shuochun | 2.00.B021 | A1 | 2017-09-25 | pass |  | 1.3.4.0
DGS-3120-24PC | Joshua | 4.00.015/3.00.522 | B1 | 2017-10-19 | failed | 和PP正在确认是否支持DHCP功能 | 1.3.4.0
DGS-3120-24SC | Joshua | 4.00.015/3.10.512 | B1 | 2017-10-19 | pass |  | 1.3.4.0
DGS-3120-24SC-DC | Joshua | 4.00.015/3.10.512 | B1 | 2017-10-26 | failed | 设备Upgrade时，进行TFTP传FW文件会由于设备重复回应确认包导致传输中断，和PP正在确认是否支持DHCP功能 | 1.3.4.0
DGS-3120-24TC | Joshua | 4.00.015 | B1 | 2017-10-26 | pass |  | 1.3.4.0
DGS-3120-48PC | Joshua | 4.00.015/3.00.522 | B1 | 2017-11-02 | failed | 设备Upgrade时，进行TFTP传FW文件会由于设备重复回应确认包导致传输中断，和PP正在确认是否支持DHCP功能 | 1.3.4.0
DGS-3120-48TC | Joshua | 4.00.015/3.00.522 | B1 | 2017-11-02 | failed | 设备Upgrade时，进行TFTP传FW文件会由于设备重复回应确认包导致传输中断，和PP正在确认是否支持DHCP功能 | 1.3.4.0
DMC-1002 | Jay | 2.03 | B1 | 2017-11-08 | failed | 设备SOID和DGS-1100-10/ME的SOID有冲突 | 1.3.4.0
DSR-1000AC | Jeff | 3.11_WW | A1 | 2017-11-16 | pass |  | 1.3.4.0
DWR-925 | Xenia |  | C1 | 2017-12-18 |  |  | 1.3.5.0
DIS-300G-8PSW | Kevin | v.1.00.003 | A1 | 2018-01-08 |  |  | 1.3.5.0
DIS-300G-12SW | Kevin | v.1.00.003 | A1 | 2018-01-15 |  |  | 1.3.5.0
DIS-300G-14PSW | Kevin | v.1.00.003 | A1 | 2018-01-15 |  |  | 1.3.5.0

## Wireless
Table description | 单元格中黑色字体FW/HW版本为PP要求DV7支持的设备版本；红色字体表示DV7已支援的设备FW/HW版本
Model | PP | FW | HW | Schedule | Status | Fail Note | D-View 7 Beta Ver. | PIC | Note
DAP-2660 | Jovi | v1.15rc119 | A | 2017-08-01 | pass |  | 1.3.4.0 |  | log: Dev FW:v1.15rc093; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-2695 | Jovi | v1.20rc091 | A | 2017-08-07 | pass |  | 1.3.4.0 |  | log: Dev FW:v1.20rc075; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-2230 | Jovi | v1.05rc031 | A | 2017-08-07 | pass |  | 1.3.4.0 |  | log: Dev FW:v1.05rc029; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-2360B | Jovi | v2.10rc054 | B | 2017-08-14 | pass |  | 1.3.4.0 |  | log: Dev FW:v2.10rc050; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. 2.After Upgrade FW by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-2310B | Jovi | v2.10rc038 | B | 2017-08-14 | pass |  | 1.3.4.0 |  | log: Dev FW:v2.10rc036; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. 2.After Upgrade FW by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-3662 | Jovi | v1.05rc047 | A | 2017-08-21 | failed | Web Status的SNMP值正确下发之后，设备需要手动重启后执行 | 1.3.2.0
DAP-3662EU | Jovi | v1.05eurc046 | A | 2017-08-21 | failed | Web Status的SNMP值正确下发之后，设备需要手动重启后执行 | 1.3.2.0
DAP-2330 | Jovi | v1.10rc035 | A | 2017-08-28 | pass |  | 1.3.4.0 |  | log: Dev FW:v1.10rc034; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. 2.After Upgrade FW by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-2690B | Jovi | v3.20rc113 | B | 2017-08-28 | pass |  | 1.3.4.0 |  | log: Dev FW:v3.20rc106; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-3320 | Jovi | v1.05rc019 | A | 2017-09-04 | failed | Web Status的SNMP值正确下发之后，设备需要手动重启后执行 | 1.3.2.0 |  | log: Dev FW:v1.05rc019; Status:Fail 1.After set Web Status by SNMP, user need to reboot device manually. DV7:1.3.2.0
DAP-2553 | Jovi | v3.10rc031 | B | 2017-09-04 | failed | Web Status的SNMP值正确下发之后，设备需要手动重启后执行；SNMP下发FW Upgrade后，设备可以通过TFTP下载FW。但是随后设备的Web GUI登不上，SNMP不通，设备可以一直ping通。需要手动重启设备后，发现FW已经Upgrade成功。 | 1.3.2.0
DWP-2360 | Jovi | v2.10rc020 | B | 2017-09-11 | failed | Web Status的SNMP值正确下发之后，设备需要手动重启后执行；SNMP下发FW Upgrade后，设备可以通过TFTP下载FW。但是随后设备的Web GUI登不上，SNMP不通，设备可以一直ping通。需要手动重启设备后，发现FW已经Upgrade成功。 | 1.3.2.0